## Sheet1
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes | 20% | 40% | 80% | 100%
Create Wireframes or sketches of your website layout | P1 | Aftab Uddin | Completed | 2025-09-20 | 2025-09-24 | 1
Design rough layouts for homepage, product page, cart, and checkout pages. | P1 | Aftab Uddin | Completed | 2025-09-21 | 2025-09-25 | 1
Define placement for navigation menus, banners, product grids, and CTA (call-to-action) buttons. | P1 | Aftab Uddin | Completed | 2025-09-22 | 2025-09-26 | 1
Use tools like Figma, Adobe XD, or pen-and-paper sketches. | P1 | Aftab Uddin | Completed | 2025-09-23 | 2025-09-27 | 1
Ensure responsive design ideas (desktop, tablet, mobile). | P2 | Aftab Uddin | Completed | 2025-09-24 | 2025-09-28 | 1
Design navigation flow, product pages, etc | P1 | Aftab Uddin | Completed | 2025-09-25 | 2025-09-26 | 2
Create a site map showing main pages (Home, Shop, Cart, Checkout, Contact). | P1 | Aftab Uddin | Completed | 2025-09-26 | 2025-09-27 | 2
Define URL structure (e.g., /products, /cart, /checkout). | P2 | Aftab Uddin | Completed | 2025-09-27 | 2025-09-28 | 2
Ensure logical flow from product browsing → product details → adding to cart → checkout | P1 | Aftab Uddin | Completed | 2025-09-28 | 2025-09-29 | 2
Design product filtering, search, and sorting features. | P1 | Aftab Uddin | Completed | 2025-09-29 | 2025-09-30 | 2
Frontend, Backend + Database development Mockups - HTML, CSS, MySQL, PHP | P1 | Aftab Uddin | In progress | 2025-09-27 | 2025-09-28 | 3
Frontend mockups using HTML/CSS to visualize user interface elements. | P1 | Aftab Uddin | In progress | 2025-09-28 | 2025-09-29 | 3
Backend mockups using PHP for routing and data handling | P1 | Aftab Uddin | In progress | 2025-09-29 | 2025-09-30 | 3
Database mockups in MySQL for schema relationships and queries. | P1 | Aftab Uddin | In progress | 2025-09-30 | 2025-10-01 | 3
Integrate UI elements with backend placeholders to simulate interaction. | P1 | Aftab Uddin | In progress | 2025-10-01 | 2025-10-02 | 3
Plan Database Schema - Users, Products, Categories, Orders, Payments | P1 | Aftab Uddin | In progress | 2025-09-29 | 2025-10-15 | 4
Users: user_id, name, email, password, address, role. | P1 | Aftab Uddin | In progress | 2025-09-30 | 2025-10-16 | 4
Products: product_id, name, category_id, price, description, stock, image. | P1 | Aftab Uddin | In progress | 2025-10-01 | 2025-10-17 | 4
Categories: category_id, name. | P2 | Aftab Uddin | In progress | 2025-10-02 | 2025-10-18 | 4
Orders: order_id, user_id, total_amount, status, date. | P2 | Aftab Uddin | In progress | 2025-10-03 | 2025-10-19 | 4
Payments: payment_id, order_id, amount, method, status. | P1 | Aftab Uddin | In progress | 2025-10-04 | 2025-10-20 | 4
Convert UI designs in HTML + CSS + JS code | P1 | Aftab Uddin | In progress | 2025-10-15 | 2025-10-18 | 4
Implement responsive grid layout with CSS Flexbox or Grid. | P2 | Aftab Uddin | In progress | 2025-10-16 | 2025-10-19 | 4
Add animations or transitions for better user experience. | P2 | Aftab Uddin | In progress | 2025-10-17 | 2025-10-20 | 4
Use JavaScript for dropdown menus, modals, sliders, and dynamic interactions. | P2 | Aftab Uddin | In progress | 2025-10-18 | 2025-10-21 | 4
Validate input forms and handle UI events (e.g., “Add to Cart” buttons). | P2 | Aftab Uddin | In progress | 2025-10-19 | 2025-10-22 | 4
Setup server-side logic for: User Authentication, Product Management, Cart functionalities | P2 | Aftab Uddin | Not started | 2025-10-17 | 2025-10-25 | 4
Implement user registration and login using PHP sessions and password hashing. | P2 | Aftab Uddin | Not started | 2025-10-18 | 2025-10-26 | 4
Create admin panel for adding/updating/deleting products. | P2 | Aftab Uddin | Not started | 2025-10-19 | 2025-10-27 | 4
Manage cart sessions for storing selected products temporarily. | P3 | Aftab Uddin | Not started | 2025-10-20 | 2025-10-28 | 4
Enable CRUD operations for users and products. | P3 | Aftab Uddin | Not started | 2025-10-21 | 2025-10-29 | 4
Design system for user-based database manipulation and cart system using CRUD operations + php | P2 | Aftab Uddin | Not started | 2025-10-24 | 2025-11-12 | 4
Create: Add new users, products, and orders to the database. | P2 | Aftab Uddin | Not started | 2025-10-25 | 2025-11-13 | 4
Read: Retrieve data for product listings, cart items, user info. | P2 | Aftab Uddin | Not started | 2025-10-26 | 2025-11-14 | 4
Update: Modify quantities, update profiles, change order statuses. | P2 | Aftab Uddin | Not started | 2025-10-27 | 2025-11-15 | 4
Delete: Remove products or clear cart. | P3 | Aftab Uddin | Not started | 2025-10-28 | 2025-11-16 | 4
Implement security measures like prepared statements to prevent SQL injection. | P3 | Aftab Uddin | Not started | 2025-10-29 | 2025-11-17 | 4
Complete Home Page - HTML + CSS | P2 | Aftab Uddin | In progress | 2025-11-14 | 2025-11-18 | 5
Include banner section, featured products, and categories. | P2 | Aftab Uddin | In progress | 2025-11-15 | 2025-11-19 | 5
Add navigation menu and footer. | P2 | Aftab Uddin | In progress | 2025-11-16 | 2025-11-20 | 5
Optimize for SEO with semantic HTML tags. | P3 | Aftab Uddin | In progress | 2025-11-17 | 2025-11-21 | 5
Include links to login, shop, and contact pages. | P1 | Aftab Uddin | In progress | 2025-11-18 | 2025-11-22 | 5
Complete Info + Details Page | P3 | Aftab Uddin | In progress | 2025-11-19 | 2025-11-23 | 5
Use dynamic PHP scripts to fetch product data by ID. | P1 | Aftab Uddin | In progress | 2025-11-20 | 2025-11-24 | 5
Show product image, name, description, price, and “Add to Cart” button. | P1 | Aftab Uddin | In progress | 2025-11-21 | 2025-11-25 | 5
Add related products or recommendations. | P1 | Aftab Uddin | In progress | 2025-11-22 | 2025-11-26 | 5
Contact Info Page - HTML + CSS + JS | P3 | Aftab Uddin | In progress | 2025-11-23 | 2025-11-28 | 5
Include contact form with name, email, and message fields. | P2 | Aftab Uddin | In progress | 2025-11-24 | 2025-11-29 | 5
Use JavaScript validation for form inputs. | P1 | Aftab Uddin | In progress | 2025-11-25 | 2025-11-30 | 5
Optionally integrate a backend PHP mailer (e.g., PHPMailer) to send inquiries. | P2 | Aftab Uddin | In progress | 2025-11-26 | 2025-12-01 | 5
Add map or social media links. | P2 | Aftab Uddin | In progress | 2025-11-27 | 2025-12-02 | 5
Payment Details Page - MySQL Workbench + PHP + Database Management | P3 | Aftab Uddin | Not started | 2025-11-27 | 2025-12-02 | 5
Create payment form with total amount, payment method, and confirmation button. | P1 | Aftab Uddin | Not started | 2025-11-28 | 2025-12-03 | 5
Use PHP to update payment and order status in MySQL database. | P1 | Aftab Uddin | Not started | 2025-11-29 | 2025-12-04 | 5
Store transaction logs in Payments table | P1 | Aftab Uddin | Not started | 2025-11-30 | 2025-12-05 | 5
Ensure secure handling of sensitive data (use HTTPS). | P1 | Aftab Uddin | Not started | 2025-12-01 | 2025-12-06 | 5
Display + Cart + User Selection Page | P2 | Aftab Uddin | In progress | 2025-12-03 | 2025-12-05 | 5
Dynamically display products in the cart using PHP session data. | P2 | Aftab Uddin | In progress | 2025-12-04 | 2025-12-06 | 5
Allow users to change quantity, remove items, or proceed to checkout. | P2 | Aftab Uddin | In progress | 2025-12-05 | 2025-12-07 | 5
Update total cost automatically using JavaScript. | P2 | Aftab Uddin | In progress | 2025-12-06 | 2025-12-08 | 5
Merging all the code together | P3 | Aftab Uddin | Not started | 2025-12-06 | 2025-12-07 | 5
Test connections between frontend, backend, and database. | P3 | Aftab Uddin | Not started | 2025-12-07 | 2025-12-08 | 5
Debug issues in form submissions, queries, or session handling. | P3 | Aftab Uddin | Not started | 2025-12-08 | 2025-12-09 | 5
Organize code in directories (e.g., /includes, /assets, /pages). | P3 | Aftab Uddin | Not started | 2025-12-09 | 2025-12-10 | 5
Implement version control (Git) for collaboration. | P3 | Aftab Uddin | Not started | 2025-12-10 | 2025-12-11 | 5
Merging Frontend + Backend development | P3 | Aftab Uddin | Not started | 2025-12-09 | 2025-12-11 | 5
Link PHP scripts to HTML forms and JS features. | P2 | Aftab Uddin | Not started | 2025-12-10 | 2025-12-12 | 5
Ensure seamless flow between UI actions and backend responses. | P2 | Aftab Uddin | Not started | 2025-12-11 | 2025-12-13 | 5
Conduct end-to-end testing (login → browse → cart → payment → confirmation). | P3 | Aftab Uddin | Not started | 2025-12-12 | 2025-12-14 | 5
Optimize for performance and responsiveness before deployment. | P3 | Aftab Uddin | Not started | 2025-12-13 | 2025-12-15 | 5